## Sheet1
Design and Implementation of a Mesh Network for IP-based,
Low Power, Wireless Communication in IoT Systems
University of Southampton
Samuel Kendall
TASK NAME | START DATE | DUE DATE | DURATION | SPRINT/MILESTONE
Working CoAP Resources with Multi-node Hopping | 2019-12-14 | 2020-01-06 | 23 | Design
Exam Revision | 2020-01-06 | 2020-01-13 | 7 | Exams
Exams | 2020-01-13 | 2020-01-24 | 11 | Exams
Implement Server and Database to Receive Data | 2020-01-24 | 2020-02-01 | 8 | Implementation
Test Server and Database | 2020-01-27 | 2020-02-02 | 6 | Testing
Design Low Power Mode (idle-wait) | 2020-02-01 | 2020-02-11 | 10 | Design
Implement Low Power Mode to Network (idle-wait) | 2020-02-11 | 2020-02-21 | 10 | Implementation
Test CoAP Nodes with Low Power Mode | 2020-02-18 | 2020-02-28 | 10 | Testing
Design Network Node Circuit with Low Power | 2020-02-28 | 2020-03-06 | 7 | Design
Working Network Node Prototype with Breadboard | 2020-03-06 | 2020-03-13 | 7 | Design
Design PCB to Implement Circuit Design | 2020-03-13 | 2020-03-23 | 10 | Design
Power Testing of Nodes on PCB | 2020-03-23 | 2020-03-30 | 7 | Testing
Construct and Test PCBs | 2020-03-30 | 2020-04-05 | 6 | Testing
Write Final Report | 2020-03-23 | 2020-04-28 | 36 | Report