## Project Risk Matrix
Invividual Projet Risk Matrix
RISK TYPE | RISK DESCRIPTION | RISK SEVERITY | RISK LIKELIHOOD | IMPACT LEVEL | RESPONSE – BEFORE – | RESPONSE – CONTINGENCY – | RISK SEVERITY KEY | RISK LIKELIHOOD KEY | RISK LEVEL KEY
External | Planned time becomes unrealistic due to other deadlines clashing | TOLERABLE | PROBABLE | HIGH | Consider expected deadlines in advanced and ensure fit around project | Reschedule project timetable and drop project sections if necessary | ACCEPTABLE | IMPROBABLE | LOW
Technical | Laptop/workstation is damaged | INTOLERABLE | IMPROBABLE | LOW | Ensure work is backed up on cloud based locations i.e. GitHub, Google Drive | Data can be restored in alternative locations from cloud services with minimal loss | TOLERABLE | POSSIBLE | MEDIUM
Organizational | Project budget exceeded | UNDESIRABLE | IMPROBABLE | LOW | Ensure that spending is planned in advanced and the cost of having to replace components is considered | Apply for additional funding from Part III budget manager | UNDESIRABLE | PROBABLE | HIGH
External | Illness | UNDESIRABLE | POSSIBLE | HIGH | Try to stay ahead of project schedule to reduce impact | Temporarily reduce workload and reschedule project accordingly | INTOLERABLE |  | EXTREME
Organizational | Project supervisor unavailable | TOLERABLE | POSSIBLE | MEDIUM | Meet regularly with supervisor to ensure up to date with likely away dates | Attempt to resolve problem via alternative sources. If not possible, move on to different project section and alter schedule accordingly
External | Part delivery late/unavailable | UNDESIRABLE | POSSIBLE | HIGH | Ensure possible alternatives to parts are selected for use in the event of unavailability | Try to find temporary alternative for part in lab. If not available, order alternative part and reschedule accordingly
Technical | Selected components do not function as expected | TOLERABLE | POSSIBLE | MEDIUM | Read through datasheets and specification of parts to ensure that they implement necessary technologies | Evalueate impact on project. Adjust project goals if small or, if large, research and order new parts and adjust schdule.
Technical | Misunderstanding of technologies in use | UNDESIRABLE | POSSIBLE | HIGH | Clarify uncertainties with supervisor before attempting to implement | Reschedule project timetable due to loss of time and drop project sections if necessary
Project Management | Project schedule becomes unrealistic due to misestimation of complexity | UNDESIRABLE | POSSIBLE | HIGH | Check with supervisor that deadlines set are realistic | Reschedule project timetable and drop project sections if necessary

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.