## Sheet1
Design and Implementation of a Mesh Network for IP-based,
Low Power, Wireless Communication in IoT Systems
University of Southampton
Samuel Kendall
TASK NAME | START DATE | DUE DATE | DURATION | SPRINT/MILESTONE
Working CoAP Resources with Multi-node Hopping | 2019-12-14 | 2020-01-06 | 23 | Design
Exam Revision | 2020-01-06 | 2020-01-13 | 7 | Exams
Exams | 2020-01-13 | 2020-01-24 | 11 | Exams
Design Low Power Mode (MAC layer) | 2020-01-24 | 2020-02-03 | 10 | Design
Implement Low Power Mode to Network (MAC layer) | 2020-02-03 | 2020-02-13 | 10 | Implementation
Test CoAP devboards with Low Power Mode | 2020-02-13 | 2020-02-23 | 10 | Testing
Add Support for SAMR30 Boards | 2020-02-23 | 2020-03-01 | 7 | Implementation
Design Network Node Circuit with Low Power | 2020-03-08 | 2020-03-11 | 3 | Design
Design PCB to Implement Circuit Design | 2020-03-11 | 2020-03-23 | 12 | Design
Coursework Week | 2020-03-23 | 2020-03-30 | 7 | Coursework
Construct and Test PCBs | 2020-03-30 | 2020-04-05 | 6 | Testing
Implement Server and Database to Receive Data | 2020-01-24 | 2020-02-01 | 8 | Implementation
Test Server and Database | 2020-01-27 | 2020-02-02 | 6 | Testing
Link nodes and Server (if time allows) | 2020-04-05 | 2020-04-12 | 7 | Implementation
Write Final Report | 2020-03-23 | 2020-04-28 | 36 | Report